## Product Backlog
Berhan Bank WSO2 Integration Platform Implementation Product Backlog
Epic | Owner | ID | User Story | Description | Acceptance Criteria
1. Integration Strategy & Governance | IT Strategy and Governance | 1.1 | As an IT strategy lead, I want to define an enterprise integration roadmap so that all initiatives are aligned with business priorities | Establish enterprise-wide integration roadmap | Roadmap documented and approved; Stakeholders aligned; Review process established
|  | 1.2 | As a governance lead, I want to define API and integration policies so that standards are enforced | Define governance and standards | Policies documented; Approval workflows defined; Compliance tracking enabled
|  | 1.3 | As a program manager, I want to track integration performance so that business value can be measured | Implement performance tracking | KPIs defined; Reporting dashboards available
2. Integration Development & Service Enablement | Innovation & Digital Strategies | 2.1 | As an integration developer, I want to build services connecting CBS and external systems so that systems communicate seamlessly | Develop integration services | Services deployed successfully; Data flow validated
|  | 2.2 | As a developer, I want reusable connectors so that development is efficient | Create reusable components | Reusable services created; Repository established
|  | 2.3 | As a system architect, I want event-driven integration so that real-time processing is supported | Enable event-driven architecture | Events processed in real time; Asynchronous flows implemented
3. API Design, Lifecycle & Governance | Solution Design and Delivery | 3.1 | As an API designer, I want to define API standards so that APIs are consistent | Define API standards | Standards documented; Templates created
|  | 3.2 | As a developer, I want to publish APIs with documentation so that consumers can integrate easily | Publish APIs | APIs published in portal; Documentation available
|  | 3.3 | As an API manager, I want to manage API lifecycle so that APIs are properly versioned | Manage API lifecycle | Versioning implemented; Lifecycle stages enforced
4. Quality Assurance & Validation | Solution Design and Delivery | 4.1 | As a QA engineer, I want automated testing so that integrations meet quality standards | Implement QA framework | Automated tests executed; Coverage threshold met
|  | 4.2 | As a tester, I want testing pipelines so that releases are validated efficiently | Enable testing pipeline | CI-integrated testing; Defects tracked
|  | 4.3 | As a business user, I want to validate solutions so that they meet business needs | Perform UAT | UAT completed; Sign-off obtained
5. WSO2 Platform Administration | API & Integration Management | 5.1 | As an admin, I want to configure the WSO2 platform so that services can be deployed | Platform setup | Platform installed; Configuration validated
|  | 5.2 | As an admin, I want to manage environments so that deployments are controlled | Environment management | Dev/Test/Prod separated; Stable deployment process
|  | 5.3 | As an operations engineer, I want backup and recovery so that services are protected | Backup and DR | Backup tested; Recovery successful
6. Infrastructure & Environment Management | Infrastructure & Cloud Administration | 6.1 | As an infrastructure engineer, I want scalable infrastructure so that demand is supported | Enable scalability | Auto-scaling configured; Load handled successfully
|  | 6.2 | As an engineer, I want high availability so that services remain uninterrupted | Ensure availability | HA setup implemented; No single point of failure
|  | 6.3 | As an engineer, I want disaster recovery so that continuity is ensured | Implement DR | DR plan tested; RTO/RPO met
7. DevOps, CI/CD & Release Management | Corporate Systems Management | 7.1 | As a DevOps engineer, I want CI/CD pipelines so that deployments are automated | Implement CI/CD | Pipelines functional; Automated deployment working
|  | 7.2 | As a developer, I want rollback mechanisms so that failures can be resolved quickly | Enable rollback | Rollback tested; Versioning implemented
8. Security, IAM & Compliance | IT Security | 8.1 | As a security officer, I want security policies so that integrations are protected | Define policies | Security policies approved; Enforcement mechanisms in place
|  | 8.2 | As a system, I want authentication and authorization so that access is controlled | Implement IAM | OAuth/JWT implemented; Access control enforced
9. Monitoring, Incident & Operations |  | 9.1 | As an operations engineer, I want monitoring dashboards so that system health is visible | Monitoring setup | Dashboards available; Metrics tracked
|  | 9.2 | As a support team member, I want alerts so that incidents are detected early | Alerting system | Alerts configured; Incident response in place
10. Capacity & Performance Management |  | 10.1 | As an infrastructure manager, I want capacity monitoring so that performance is maintained | Monitor capacity | Load testing completed; Capacity plan documented
11. Business Engagement & Demand Management | Digital Banking Business | 11.1 | As a business stakeholder, I want to submit requirements so that needs are captured | Manage demand intake | Backlog maintained; Requirements documented
|  | 11.2 | As a business user, I want to validate solutions so that requirements are met | Business validation | Acceptance criteria met; UAT signed off
12. Partner & Ecosystem Integration | Digital Banking Business | 12.1 | As a partner, I want secure API access so that I can integrate with the platform | Partner access | Secure API access granted; Integration successful
|  | 12.2 | As a platform owner, I want onboarding processes so that integrations are standardized | Partner onboarding | Onboarding process defined; Partners integrated
13. Knowledge Transfer & Capability Building | Cross-functional | 13.1 | As a team member, I want training so that I can operate the platform | Training delivery | Training completed; Materials documented
|  | 13.2 | As an organization, I want documentation so that knowledge is retained | Documentation | SOPs available; Knowledge base created
31

## Objective and Scope
WSO2 Enterprise Integration
Objective
The goal is to implement a WSO2-based enterprise integration and API management platform
Secure connectivity
Scalable architecture
API-driven integration across channels and backend systems
Scope of Implementation
A. API Management Layer (WSO2 API Manager)
API publishing and lifecycle management
Version control (v1, v2, etc.)
Developer portal for partners
Throttling and rate limiting
API security enforcement
B. Integration & Orchestration (WSO2 Micro Integrator)
Service orchestration workflows
Routing logic (channels, transactions, partners)
Data transformation:
JSON ↔ XML
REST ↔ SOAP
Integrations with:
Core banking (Rubikon)
Switch systems (IPS)
Payment partners
C. Identity & Security (WSO2 Identity Server)
OAuth2 / OpenID Connect
Multi-Factor Authentication (MFA)
Role-Based Access Control (RBAC)
Tokenization and encryption
API-level security policies
D. Monitoring & Observability
Centralized logging
Transaction tracking
Audit compliance
Performance monitoring (ELK / Grafana-ready)
E. Migration Scope
Migration of existing integrations, including:
eTax
ET-Flight
Safaricom
M-Pesa
Telebirr, etc.
F. DevOps & Deployment
Environment setup:
DEV, SIT, UAT, PROD
CI/CD pipeline
High availability (Active-Active / Disaster Recovery)
G. Testing & Deployment
SIT & UAT support
Performance testing
Production deployment
Hypercare support